## Construction Report
DASD
Primary | Facility Type | Description | Website | Budget ($) | Actual Start Date | Actual Finish Date
Fire Station 26 (AR1916) (C19-401) | Fire Station | New Firestation. |  | 11578900 | 2018-12-18 08:00 | 2025-02-14 17:00
Willard Garage Phase III (AR1904) (C20-320) | Parking Garage | South wall water infiltration |  | 1457731 | 2019-04-02 08:00 | 2023-09-24 17:00
League Park PH II- Lighting & Scoreboard (C20-307) (C19-119) | Parks-Playgrounds | Lighting, scoreboard, dugout covers |  | 932250 | 2019-09-24 08:00 | 2023-06-16 17:00
Heritage Park 2 West Bank (C21-315) | Parks-Playgrounds | Full park design and renovation. |  | 1250000 | 2018-12-10 08:00 | 2024-03-19 17:00
2022 Court Repairs: Kerruish Park (SD2202) | Parks-Playgrounds | Court Repairs @ Kerruish Park |  | 326628.75 | 2022-11-14 08:00 | 2024-06-05 17:00
Parks and Recreation Plan | Parks-Playgrounds |  |  | 616928
US Soccer Foundation Mini-Pitch (SD2308) | Parks-Playgrounds
PSTC @ South High (AR2315) | Police Station
West Side Market Vendor Stations (AR1915a) (C20-319) | Public Facility | Renovation of all vendor stalls in the main Market House. |  | 1836890 | 2020-05-05 08:00 | 2025-05-18 17:00
West Side Market Elevator Replacement (AR1915d) | Public Facility |  |  | 1250000 | 2021-08-25 08:00 | 2024-10-07 17:00
WSM Shared Prep Room | Public Facility |  |  | 477415 | 2019-09-17 08:00 | 2023-05-15 17:00
WSM Boiler Room Concrete Repair | Public Facility
WSM Clock Tower Masonry (C19-319) | Public Facility |  |  | 1881000 | 2020-03-26 08:00 | 2023-08-31 17:00
2021 Public Safety Roofs (AR2120) (C21-408) | Public Safety | Roof replacement and envelope repairs for FS 13, 28 and 33. |  | 2047782 | 2021-05-07 08:00 | 2024-04-03 17:00
Lonnie Burten Recreation Center Renovation PH I Exterior, Masonry, Pool, & Windows (AR1927c) (C19-315) | Recreation Center | Design for complete facility renovation. |  | 2447170 | 2019-02-21 08:00 | 2023-10-05 17:00
Cudell & Fairfax Rec Center Roofs | Recreation Center | Roof replacement and envelope repairs |  | 3945905 | 2020-05-05 08:00 | 2024-09-25 17:00
Clark Recreation Center Renovation (AR1927a) (C19-313) | Recreation Center | Complete facility renovation. |  | 6650270 | 2018-12-17 08:00 | 2023-09-29 17:00
Central Rec Phase 3 (Pool, Electrical & Interior Imp.) (C14-310) | Recreation Center |  |  | 3545520 | 2017-05-29 08:00 | 2024-10-21 17:00
Thurgood Marshall 2019 Improvements Re-Bid (AR1902) (C18-313) | Recreation Center | Site circulation and access improvements for baseball fields.. |  | 577122.16 | 2018-08-31 08:00 | 2024-04-06 17:00
Engineering & Construction
Primary | Facility Type | Description | Website | Budget ($) | Actual Start Date | Actual Finish Date
Center Street Swing Bridge SFN 109597 | Bridge | electrical, mechanical, structural and painting improvements. | https://www.transportation.ohio.gov/projects/projects/109597 | 6158631.4 | 2019-02-04 08:00 | 2023-07-30 17:00
East 75th St Bridge over NS & GCRTA (PID 106378) | Bridge | Rehabilitation of bridge over Norfolk Southern Rail Road and Greater Cleveland RTA. | https://www.transportation.ohio.gov/projects/projects/106378 | 6178177.13 | 2019-04-30 08:00 | 2024-04-13 17:00
East 185th (Nottingham to Lakeshore) | Roads | Road rehabilitation improvement. | http://east185streetscape.com/ | 13342585.79 | 2019-09-19 08:00 | 2023-10-15 17:00
South Moreland, Shaker Square and North Moreland Improvement (Griffing to Larchmere) (C21-214) | Roads | Road rehabilitation improvement. | https://www.northandsouthmoreland.com/ | 7588074 | 2020-11-02 08:00 | 2024-06-12 17:00
Euclid Ave Resurfacing (Ivanhoe to Upper Valley) | Roads | Road rehabilitation improvement. | https://www.transportation.ohio.gov/projects/projects/110942 | 2300000 | 2021-10-28 08:00 | 2023-06-30 17:00
West Franklin (West 85th to West 25th) (PID114532) | Roads | Road rehabilitation improvement. | https://westfranklincle.com/ | 3806048.29 | 2020-03-20 08:00 | 2023-08-31 17:00
E. 140th Rehabilitation (St Clair to Lakeshore) | Roads | Road rehabilitation improvement. | https://www.east140streetscape.com/ | 9378785 | 2020-11-04 08:00 | 2024-07-25 17:00
Ridge Road (Flowerdale to Brookpark) | Roads | Road rehabilitation improvement. | https://cuyahogacounty.us/publicworks/planning-programming/projects-programs/projects-and-programs---old/ridge-road---pearl-road-to-flowerdale-avenue | 4460000 | 2020-10-19 08:00 | 2023-08-18 17:00
Brookpark Rd (SR 17) (W 130th to I480) PID 89267 | Roads | Road rehabilitation improvement. | https://www.transportation.ohio.gov/about-us/traffic-advisories/district-12/cuyahoga-county-construction-update | 4500000 | 2021-06-17 08:00 | 2024-11-15 17:00
E. 79th Rehabilitation (Woodland to Chester) (C21-206) | Roads | Road rehabilitation improvement. |  | 3937751.21 | 2020-10-19 08:00 | 2023-08-29 17:00
Frank (E 101st to 105th) | Roads | Innovation Square, Phase I construction of new streets from East 101. |  | 2100000 | 2018-06-14 08:00 | 2024-07-29 17:00
Hudson Ave Extension (E. 105th to E. 101st) | Roads | Innovation Square, Phase II construction of new streets from East 105. |  | 1814414.36
Hill International - DEOG works | Roads |  |  | 827999.29 | 2022-06-06 08:00 | 2023-11-19 17:00
Circle Square, Phase 1A (Chester Ave and the western portion of Reserve Court) | Roads |  |  | 577276.15 | 2020-03-16 08:00 | 2023-07-28 17:00
Lorain (W 25th & Hope Bridge) | Roads |  |  | 679700
Ridge Rd (Memphis to Denison) | Roads |  |  | 2200000
2021 Requirement Contract - Part 4 Horizontal Sidewalk Cutting | Sidewalks |  |  |  | 2022-04-06 08:00 | 2022-10-02 17:00
2021 Requirement Contract - Part 5 TDS East Side | Sidewalks |  |  |  | 2022-05-19 08:00 | 2023-11-01 17:00
2021 Requirement Contract - Part 6 TDS West Side | Sidewalks |  |  |  | 2022-05-19 08:00 | 2023-11-01 17:00
2021 Tree Damaged Sidewalks | Sidewalks |  |  |  | 2022-06-06 08:00 | 2023-11-19 17:00
50/50 Sidewalk Program (DOS) | Sidewalks |  |  | 723061.38

## Comments
Row 2 | Inspection of W 3rd is scheduled for Wednesday July 19th. Inspection of Carter for July 20th is cancelled because of no CCR for Mod 2 of ELR Inspection Contract. Inspection will become overdue after July 23, 2023. | Larry Ho | 07/17/23 12:22 PM
Row 2 | Larry, The 2023 FCM date is missing in AssetWise. FHWA will cause Ohio to become non-compliant if the inspection was not performed prior to 6/5/2023. Please update Assetwise ASAP. Regards, Omar Abu-Hajar, P.E. , MSCE-Structures NBIS Compliance/Municipal Bridge Program Manager ODOT Office of Structural Engineering 3rd Floor - Mail Stop 5180 1980 West Broad Street, Columbus, Ohio 43223 Tel: 614-387-1257 (Office) 614-579-8120 (Cell) Fax: 614-887-4047 Structural Engineering ¦ Ohio Department of Transportation | Larry Ho | 07/17/23 12:18 PM
Row 2 | @lho@city.cleveland.oh.us please send Rick copy of letter from ODOT | Clay Harris | 07/14/23 1:55 PM
Row 2 | Eagle Photos will be hand delivered to City 3-28-22. Lower chord of Lift Span Truss needs immediate maintenance. Lift Span is missing upper span locks. Lift Span swings like pendulum on counterweight cables. Consultant is providing estimated costs for repairs and for demolition costs. | Larry Ho | 03/28/22 12:29 PM
Row 2 | Euthenics to complete Willow Top chord inspection this week and this is the final field task of the contract. Consultant ELR when queried as to when the first report are to be delivered, they cited that their subs are the causes for the delays. | Larry Ho | 11/11/21 10:59 AM
Row 2 | ODOT provided access to Assetwise Database for the moveable bridges to be inspected 6-2-21 for our consultant E.L. Robinson | Larry Ho | 06/03/21 9:24 AM
Row 2 | Execution of Agreement with Design Consultant. Received partially executed agreement 3-18-21. NTP issued 3-5-21. | Larry Ho | 03/25/21 12:58 PM
Row 3 | Need to postpone contract due to long lead time for epoxy paint. | Clay Harris | 07/26/22 1:50 PM
Row 3 | @dortmanii@city.cleveland.oh.us @rswitalski@city.cleveland.oh.us please provide Certificate of insurance for this project | Clay Harris | 05/27/21 1:39 PM
Row 3 | Prepare decision memo once scope is determined | Clay Harris | 09/05/19 1:40 PM
Row 4 | @mbramley@clevelandohio.gov please set up meeting w/ Rick, Larry, & Ron to discuss letter to ODOT | Clay Harris | 04/21/23 3:02 PM
Row 4 | The abandoned NEORSD sewer collapsed during pile driving operations within the work area. ODOT demobilized the project for 83 days to mitigate this obstruction. This mitigation resulted in about $210,000 of extra costs. These extra costs per ODOT is the responsibility of the City because this project is capped for federal funding. The City is going to send ODOT a letter to dispute that these extra costs was not of the City's making; the project should not have been demobilized; ODOT should have referenced ORC 5515.02 which allowed the Director of Transportation to issue a notification to the affected utility owner to remove this utility obstruction within 5 days and if not done so, the Director would take the appropriate measures to remove this obstruction and to recover the incurred costs. When and if we get a billing for these costs, the City should refuse to pay these costs for these reasons.. | Larry Ho | 02/24/23 3:34 PM
Row 4 | Sewer collapsed and project has been stoped. ODOT need to determine who owns sewer and get it repaired before we can re-start bridge work. | Clay Harris | 07/26/22 1:51 PM
Row 4 | CPP scheduled to come in to install four new power poles. JDW will complete temporary wire relocations and CPP will re-energize the relocated wires. April 8 & (, JDW intends to install Railroad protective Structure over GCRTA tracks if they can secure the requested outage dates. Contractor is casting new retaining caps & parapets. Contractor is building scaffolding under bridge for deck demolition over NS Corp tracks. ODOT secured City's concurrence on creating a change order for RR Pro to perform NS flagging because NS is unable to supply flaggers. Footings for GCRTA Protective Shelter has been completed. | Larry Ho | 03/28/22 12:24 PM
Row 4 | @lho@city.cleveland.oh.us Contractor having issues getting permit from RTA to demo bridge. Prepare summary for Director review to forward to Chief Puente. | Clay Harris | 03/15/22 1:41 PM
Row 4 | @lho@city.cleveland.oh.us Please send contractor notice for waterline shut off to Rick & Director | Clay Harris | 01/28/22 9:23 AM
Row 4 | JDW has moved the bridge closure date to 1-3-2022. This delay is a resulting of NSRR not granting ROE to them for entering their property to demolish the bridge. CPP has changed their temporary pole locations. This is resulting in an increase in longer power cables to be bought under the contract. AT & T pre-phase relocation start date is unknown. DEOG capped off the gas line to the bridge and accidentally cut off supply to Orlando bread Factory. NSRR us seeking a precon on site before it would consider issuing ROE to JDW. | Larry Ho | 12/10/21 10:11 AM
Row 4 | ODOT has been very active engaging CWD on the E 75th Street Bridge Reconstruction. depending on the outcome of the pressure test last Sunday on the new OC3 feed to the Orlando Bakery, CWD will let the City know if the Temporary Waterline bypass can be non-performed, The CWD is at Grand Avenue. The E75th Street Feed to Orlando with the 2 valves in question has been confirmed by CWD as inactive and therefore no longer a concern. 15 RFIs related to utilities have been answered to date and a few on steel fabrication. The north haul road is NS Service Road-E76th-Dell-E75th-Woodland Ave. The south haul road is E75th-Kinsman-E79th-Woodland. School board is aware of Bridge closing 11-15-2021 through 5-31-2023 (an environmental commitment step) | Larry Ho | 11/11/21 10:48 AM
Row 4 | Consultant researching how to get Orlando Bakery water during temp shutoff. | Clay Harris | 10/07/21 1:36 PM
Row 4 | CPP is non responsive to relocate utilities. Work is becoming critical to project schedule. Need help getting them off the dime. | Clay Harris | 06/03/21 1:38 PM
Row 4 | Rick asks to reach out to CPP to perform their relocation work ahead of the 8-12-21 bid date. Numerous emails and voicemails and Piggyback Utilities for details and schedule of the CPP relocation status have gotten no response. CPP relocation is first critical path item to the complicated phase demolition of the bridge. Potential to big delay claims. Remember we are at the mercy of the new hurricane season and our request for early work is not unreasonable and the potential delay totally avoidable since ODOT has already issued early warning to the City for the Railroad Permit to be secured prior to bid date. | Larry Ho | 06/03/21 9:54 AM
Row 4 | Waiting for Orlando Payment Check of $13,330 for Parcel T-1 Purchase. Goal is to achieve ROW for sale of this project. | Larry Ho | 03/25/21 12:52 PM
Row 4 | ROW Clearance is last obstacle to filing, This was scheduled for 1-15-20. Because of the Covid and many agencies board of directors are holding only monthly meetings to approve offers, we could anticipate a minor delay in this process. But there is float in our schedule for sale. | Larry Ho | 12/04/20 2:08 PM
Row 4 | Anticipate 12-1-20 Environmental Clearance. Anticipate early March for ROW Clearance. Stage III have been resolved with ODOT. A new utility Crown Castle Fiber Installation was discovered as needing relocation and currently we will need their plans to be added to the project. PSE is dependent on ROW Clearance. | Larry Ho | 11/20/20 3:10 PM
Row 4 | Both NSRR & GCRTA Construction Agreements were given to KMJM for use in ROW acquisition Offer phase. Issue I grant application for $2.3M submitted 11-5-20 . Awaiting Office of Communications approval of responses to questions from Public Input Phase of the project. This is final requirement for Environmental Clearance Certification. Awaiting City Ownership Deed for recently purchased ORFAM Parcel at SE corner of bridge. Consultant have provided resolution of Stage 3 plan comments from ODOT & City. | Larry Ho | 11/06/20 2:04 PM
Row 4 | Euthenics provided Stage 3 disposition comments to ODOT. | Larry Ho | 10/29/20 12:14 PM
Row 4 | TE provided Stage 3 Comments. NSRR & A&T left to comment. | Larry Ho | 10/23/20 1:16 PM
Row 4 | One community advocate commented on E 75th Street Public Input Press Release with multiple comments from consideration of community needs to diversity hiring of minorities and women. Draft response is being reviewed prior to submitting to this interested party. Received ODOT Stage 3 Comments Roadway, bridge & Utilities Comments 10-2-20. Central Office Geotech Comments received questioning Abutment Foundation design and City's preference to seat the single pier foundation of 15 piles on rock that is 20 feet from that of friction pile design contrary to using friction piles. | Larry Ho | 10/08/20 9:46 AM
Row 4 | 9-24-20 Meeting held with CPP & Verizon. They agreed to share same bay for conduit placement. CPP refused to share manhole with Verizon, forcing Verizon will use large pullbox at each end of the bridge. Verizon & CPP will share temporary overhead crossings during construction. CPP will initiate crossing upon the final completion of their design. received ODOT Stage 3 review comments 10-2-20. one comment received for Public Input process which concludes 10-4-20. Letter of supports requests for funding application use were issued to various stakeholders and interested parties. GCRTA construction agreement pending. The September Posting & Traffic has resulted in an NBI sufficiency rating of 29% well below the 50% threshold needed for funding consideration. | Larry Ho | 10/02/20 3:28 PM
Row 4 | Anticipate completion GCRTA construction agreement since Stage 3 comments are very minor and GCRTA has confirmed support for the project this morning. | Larry Ho | 09/25/20 12:22 PM
Row 4 | Received Resolution of City and ODOT Stage 2 Review Comments 5-22-20. | Larry Ho | 05/22/20 11:53 AM
Row 4 | ODOT established 8-1-20 as date for Environmental Document Approval based on the drilling for the ESA II that is happening this week to be followed by RMR and C2 Reviews and Approval. | Larry Ho | 04/20/20 10:09 AM
Row 4 | Anticipate Combined Stage 2/3 Submittal 8/10/2020. CPP & CWD input needed for final plan development. all other utilities have bought into the proposed relocation scheme for final plans development. ROW Acquisition authorized 3/20/20. OES to determine the sites needing ESA II. | Larry Ho | 03/22/20 5:31 PM
Row 4 | NSRR partially executed agreement was hand delivered to ODOT D-12 3-18-20. | Larry Ho | 03/19/20 12:43 PM
Row 4 | ODOT has mailed Mike Schipper @ GCRTA originals of partially executed agreement for their final execution. | Larry Ho | 03/19/20 12:41 PM
Row 4 | Authorization given to Euthenics to proceed with Revised Stage 2 Design for an additional service amount of $117,677. This amount is to be paid from the existing available balance. Latest design schedule shows Concurrence Stage 2 Design delivery date as 3/2/2020. | Larry Ho | 01/09/20 3:34 PM
Row 4 | Where ODOT $135k contribution? | Clay Harris | 10/31/19 1:34 PM
Row 4 | Proposal to re-submit Stage 2 with reduced project limits and bridge cross-section while maintaining same profile and foundation types. CWD & CPP will have to share one bay of the bridge.. This proposal will save $1M from the previous submittal. New estimate puts project at about $6M. Euthenics to provide revised schedule and proposal for a modification to perform the changes. | Larry Ho | 09/26/19 12:48 PM
Row 4 | @lho@city.cleveland.oh.us Coordinate Traffic Eng. request for 10 ft wide sidewalks | Clay Harris | 07/18/19 1:37 PM
| no money | Clay Harris | 09/12/19 1:35 PM
Row 4 | Stage II issues with CPP, WPC. ODOT cautions that CPP 16' chamber will be considered a bridge per ORC definition, hence there needs to be designed as a bridge , inventory, inspected and maintained. Prime . WPC will not maintain yard drain as designed. Consultant informed the City additional design costs for ecological studies and ESAII and additional ROW services for un-scoped takes. ODOT suggested City write letter to state the existing encroachments into the railroad properties will remain unchanged | Larry Ho | 07/11/19 12:16 PM
Row 4 | Coordinate road between OC3 & bridge limits | Clay Harris | 01/24/19 1:44 PM
Row 4 | Coordinate RR agreement w/ LAW | Clay Harris | 01/24/19 1:41 PM
Row 4 | Sent MOU to RR. They are non responsive. Rick to contact executives. | Clay Harris | 09/06/18 1:46 PM
| Complete | Clay Harris | 12/13/18 1:40 PM
Row 4 | Confirm NOACA funding | Clay Harris | 11/08/18 1:47 PM
Row 4 | Notify WPC of damage to approach slabs @ bridge. | Clay Harris | 08/30/18 1:42 PM
| complete | Clay Harris | 09/06/18 1:46 PM
Row 6 | @jrose@clevelandohio.gov please check w/ purchasing on Fegahlli contract | Clay Harris | 01/27/22 2:55 PM
Row 8 | @mmcandrews@city.cleveland.oh.us please have contractor update project schedule | Clay Harris | 05/27/21 7:51 AM
Row 9 | @mreder@city.cleveland.oh.us Please take a look a preliminary schedule & let me if you have any questions or concerns. Thanks | Clay Harris | 11/30/18 3:14 PM
Row 11 | @cedman@clevelandohio.gov CM is interested in ground breaking ceremony for project. Please provide project fact sheet. | Clay Harris | 08/17/22 9:02 AM
Row 11 | @jmcknight@city.cleveland.oh.us Please take a look a preliminary schedule & let me if you have any questions or concerns. Thanks | Clay Harris | 11/30/18 3:14 PM
Row 13 | @jmcknight@city.cleveland.oh.us @cedman@clevelandohio.gov Send contact info for Cityworks & GIS to Jay | Clay Harris | 12/16/21 8:07 AM
Row 14 | @cedman@clevelandohio.gov @jrauschenbach@clevelandohio.gov please coordinate w/ streets Dept. | Clay Harris | 11/14/22 10:18 AM
Row 14 | @jrauschenbach@clevelandohio.gov please attach pics | Clay Harris | 09/27/22 10:33 AM
Row 20 | @agreen@city.cleveland.oh.us check bid experation date. | Clay Harris | 07/08/21 3:54 PM
Row 21 | @mstahl@city.cleveland.oh.us please follow up w/ Carmen regarding setting up status meeting w/ Director | Clay Harris | 01/27/22 3:02 PM
Row 21 | Need to confirm date for 2022 Capital Requests meeting | Clay Harris | 01/20/22 3:41 PM
Row 23 | @eharris2@city.cleveland.oh.us research why Mayor's report check box not linked | Clay Harris | 03/16/22 1:42 PM
Row 23 | @jrose@clevelandohio.gov please check w/ purchasing on status of contract? | Clay Harris | 01/27/22 2:36 PM
Row 25 | @eharris2@city.cleveland.oh.us move to ward 14 | Matthew Spronz | 01/22/20 3:57 PM
Row 26 | @eharris2@city.cleveland.oh.us @cedman@city.cleveland.oh.us @mduluk@city.cleveland.oh.us @rseitz@city.cleveland.oh.us Contract with Sixmo Inc is executed as of 7/19/19 | Matthew Spronz | 07/19/19 12:46 PM
| Excellent. | Carter Edman | 07/19/19 12:47 PM
Row 29 | @eoneill@clevelandohio.gov please confirm schedule for council report. Thanks | Clay Harris | 08/17/22 10:17 AM
Row 30 | @rchappelle@clevelandohio.gov please take a look at scope of repairs and provide estimate. | Clay Harris | 05/08/23 4:31 PM
Row 31 | @eoneill@city.cleveland.oh.us @rswitalski@city.cleveland.oh.us just checking on status of TA. Work is scheduled to start next week. | Clay Harris | 05/16/22 11:31 AM
Row 34 | @asanchez@clevelandohio.gov @rmason@clevelandohio.gov @eoneill@clevelandohio.gov please set up meeting with Edwins restaurant@asanchez@clevelandohio.gov @rmason@clevelandohio.gov @eoneill@clevelandohio.gov please set up meeting with Edwins restaurant@asanchez@clevelandohio.gov @rmason@clevelandohio.gov @eoneill@clevelandohio.gov please set up meeting with Edwins restaurant@asanchez@clevelandohio.gov @rmason@clevelandohio.gov @eoneill@clevelandohio.gov please set up meeting with Edwins restuarant to discuss access. | Clay Harris | 06/23/23 1:22 PM
Row 34 | @asanchez@clevelandohio.gov please prepare TA notifying public when contractor plan to start back up. | Clay Harris | 03/03/23 1:04 PM
Row 34 | @asanchez@clevelandohio.gov set up coordination meeting to address public concerns with Rick & Tom | Clay Harris | 08/23/22 1:07 PM
Row 34 | meeting canceled. Send progress update to council member. | Clay Harris | 07/12/22 1:09 PM
Row 34 | @eharris2@city.cleveland.oh.us send outlook invite for council member meeting on june 28th | Clay Harris | 05/17/22 1:04 PM
Row 34 | Planning is coordinating community outreach survey that may request additional scope. | Clay Harris | 10/14/21 1:13 PM
| Complete | Clay Harris | 01/06/22 11:13 AM
Row 35 | @asanchez@clevelandohio.gov @eoneill@clevelandohio.gov Rick needs price to relocate stone garden @ Helen Simpson Park | Clay Harris | 06/23/23 1:18 PM
| done | Clay Harris | 07/14/23 1:15 PM
Row 35 | @rmason@clevelandohio.gov please check on status of contract | Clay Harris | 04/21/23 2:35 PM
Row 35 | Follow up meeting scheduled for 9/20 | Clay Harris | 09/09/22 7:48 AM
Row 35 | Need to confirm location & date for public outreach meeting. | Clay Harris | 08/02/22 1:07 PM
| done | Clay Harris | 09/09/22 7:48 AM
Row 35 | @asanchez@city.cleveland.oh.us please follow up w/ Urban forestry and get confirmation on plans. | Clay Harris | 03/15/22 1:12 PM
Row 36 | NS RR working on construction agreement so contractor can get a permit. | Clay Harris | 01/27/23 1:05 PM
Row 36 | @erreza@clevelandohio.gov send updated fact sheet to rick and stop by to inform council member. | Clay Harris | 01/13/23 3:18 PM
| complete | Clay Harris | 01/27/23 1:04 PM
Row 36 | @rswitalski@city.cleveland.oh.us @tboyer@city.cleveland.oh.us Project passed BoC proceed to contract formation | Matthew Spronz | 07/22/21 12:15 PM
Row 37 | @erreza@clevelandohio.gov provide sf of sidewalk repairs to @eoneill@clevelandohio.gov so she can prepare estimate. | Clay Harris | 06/23/23 1:29 PM
Row 37 | confirmed that Meijer store should be opened end of June. Road project should be complete on June 2nd. | Clay Harris | 01/06/23 1:19 PM
Row 37 | @eoneill@clevelandohio.gov done | Clay Harris | 12/12/22 8:51 AM
Row 37 | @eharris2@clevelandohio.gov please separate the projects into two separate projects. Frank is in contract formation, Hudson is in stage 2 design. | Erin Oneill | 12/09/22 1:22 PM
Row 37 | @erreza@city.cleveland.oh.us need to develop schedule for administration review | Clay Harris | 03/29/22 1:05 PM
| done | Clay Harris | 05/17/22 1:21 PM
Row 37 | Director requested cost proposal for work on E 103rd(Quebec to Cedar). | Clay Harris | 02/08/22 1:09 PM
| done | Clay Harris | 03/15/22 1:16 PM
Row 37 | Consultant to redesign & submit revised plan for review on Jan 14th | Clay Harris | 01/13/22 1:28 PM
Row 37 | Reviewed plan w/ Developer to discuss access to property on corner of Hudson on 9/23. Traffic Dept. is addressing. | Clay Harris | 09/23/21 1:10 PM
| need to postpone bid | Clay Harris | 10/28/21 1:13 PM
Row 37 | CM Griffen requested project be completed before 2022. However, there are issues w/ sewer which increase project costs +/- $1.5m. Increase included on 2022 Bond requests lists. Director requested technical memo to communicate w/ Council. | Clay Harris | 06/03/21 1:21 PM
Row 37 | @eharris2@city.cleveland.oh.us test | Rick Switalski | 06/12/20 3:35 PM
Row 37 | Site restoration for property in ROW. Need to determine how best to proceed. | Clay Harris | 07/25/19 1:35 PM
| site restored according to specs. Still waiting on eminent domain decision for property in on Hudson & 103rd | Clay Harris | 12/05/19 1:10 PM
Row 37 | Need eminent domain of parcel acquisition. | Clay Harris | 07/25/19 1:33 PM
Row 37 | Need confirmation on which power utility developer selected. | Clay Harris | 01/24/19 1:09 PM
| @fkeehl@city.cleveland.oh.us please provide cost estimate for underground work | Clay Harris | 02/14/19 1:08 PM
| complete | Clay Harris | 03/22/19 2:30 PM
Row 37 | Real Estate coordinate easements w/ Fairfax CDC | Clay Harris | 09/06/18 1:42 PM
| @fkeehl@city.cleveland.oh.us provide specs Real estate for demolition in City ROW scheduled in spring 2019 | Clay Harris | 12/06/18 1:26 PM
Row 37 | Add project to MOCAP Bond List in Feb 2019 | Clay Harris | 09/21/18 3:23 PM
| pending | Clay Harris | 10/18/18 1:31 PM
Row 38 | @erreza@clevelandohio.gov Please input budget information | Erin Oneill | 07/18/23 1:49 PM
Row 38 | Need to fast track contract execution to meet development schedule. | Clay Harris | 04/14/23 1:14 PM
| done | Clay Harris | 07/14/23 1:31 PM
Row 38 | @rswitalski@city.cleveland.oh.us need a decision memo of ~$216k to cover shortfall | Clay Harris | 03/03/23 1:16 PM
Row 38 | confirm developer schedule for Meijer won't conflict w/ road construction project. | Clay Harris | 12/15/22 8:52 AM
| included with Frank | Clay Harris | 03/03/23 1:15 PM
Row 38 | @erreza@clevelandohio.gov please update project limits, budget, & schedule. Thanks | Clay Harris | 12/12/22 8:51 AM
Row 39 | need to start preparing bids to advertise in Fall. | Clay Harris | 06/23/23 2:05 PM
Row 39 | 3/22/22: Addendum #5 was sent out 3/22 at 11:55am. We are on schedule for bid opening 3/25 at noon. | Erin Oneill | 03/22/22 1:48 PM
Row 43 | Address comments from Councilman Kazy regarding wires on poles | Clay Harris | 09/05/19 1:10 PM
Row 43 | @dweglicki@city.cleveland.oh.us Please update project notes for mayor's bi-weekly report sent in previous email. | Clay Harris | 09/04/19 10:31 AM
Row 43 | Although constructed within the City Right of Way, this will be very large fast track project, particularly for Verizon, which will be affecting many locations and properties throughout the City with new utility poles. I suggest that a briefing be prepared for the Councilmembers so they know what to expect when construction of multiple new pole locations begins in the fall of this year. | Dave Weglicki | 05/15/19 4:55 PM
Row 44 | Chief wants to make sure they prioritize the replacement of the sidewalk on Euclid before the winter. | Clay Harris | 09/20/22 3:18 PM
Row 44 | Work going smoothly. Hill waiting on contract to sign. | Robert Knopf | 04/11/22 1:53 PM
Row 46 | @rmason@clevelandohio.gov check with Doug Blank and inquire how extending Stokes from Chester to Euclid would impact Circle Square | Clay Harris | 06/23/23 1:10 PM
Row 48 | @rswitalski@city.cleveland.oh.us @rchappelle@clevelandohio.gov please discuss construction phase services with Rick | Clay Harris | 07/14/23 1:27 PM
Row 48 | @erreza@clevelandohio.gov get construction phase services for consultant. | Clay Harris | 06/23/23 1:35 PM
Row 48 | @erreza@clevelandohio.gov follow up w/ ODOT & Perk to confirm TA has been issued. | Clay Harris | 06/23/23 1:33 PM
Row 48 | @erreza@clevelandohio.gov @rswitalski@city.cleveland.oh.us need to find ordinance requesting sewer district pay for MH adjustments | Clay Harris | 01/13/23 3:22 PM
Row 48 | @erreza@city.cleveland.oh.us please confirm when TLCI will be complete | Clay Harris | 05/17/22 1:12 PM
| done | Clay Harris | 07/26/22 1:17 PM
Row 49 | @erreza@clevelandohio.gov prepare TA | Clay Harris | 03/17/23 1:03 PM
| done | Clay Harris | 04/14/23 1:09 PM
Row 49 | Resident concerned that requested speed tables, raised crosswalks, & mini roundabouts. They sent letter to Mayor requesting that we postpone project. | Clay Harris | 01/13/22 1:33 PM
| Rick to draft memo for director and he will follow up w/ Council person to see how best to proceed. | Clay Harris | 01/13/22 1:34 PM
Row 49 | Completing TLCI Implementation grant application. Will send to Director for review. Due on 10/16. | Clay Harris | 10/15/20 1:17 PM
Row 50 | Provided locations for trash receptacle along project to Council member as requested. | Clay Harris | 08/01/22 9:38 AM
| done | Clay Harris | 08/02/22 1:34 PM
Row 51 | @pfatica@clevelandohio.gov please send CPP meeting invite to Rick | Clay Harris | 07/26/22 1:41 PM
| done | Clay Harris | 07/26/22 2:07 PM
| done | Paul Fatica | 07/26/22 2:09 PM
Row 51 | CM Polensik requests for E 140th TLCI Report | Clay Harris | 04/11/22 8:11 AM
Row 52 | ODOT has requested right of entry from each property owner where sidewalk work is adjacent to buildings. | Clay Harris | 07/14/23 2:00 PM
Row 52 | @pfatica@clevelandohio.gov please send issue w/ CPI to Rick | Clay Harris | 09/13/22 1:28 PM
| sent to RJS 9/13/22 | Paul Fatica | 09/13/22 2:59 PM
| Rick contacted CPI | Clay Harris | 11/01/22 1:31 PM
Row 52 | Meeting w/ council member polensick to discuss overall project status | Clay Harris | 07/26/22 1:38 PM
| done | Clay Harris | 08/02/22 1:33 PM
Row 52 | Bids over budget Received additional funds. Need to inform Euclid & ODOT by 4/8 | Clay Harris | 04/05/22 1:34 PM
Row 52 | Project scheduled for public art committee on March 11th. | Clay Harris | 03/01/22 1:45 PM
| done. | Clay Harris | 03/15/22 1:53 PM
Row 52 | Addressing comments with council man. Director to set up a follow up meeting w/ him. | Clay Harris | 03/01/22 1:43 PM
Row 52 | @pfatica@city.cleveland.oh.us Set up a follow up meeting w/ RTA & Traffic Engineering to discuss moving bus stops. | Clay Harris | 07/08/21 1:34 PM
| @rswitalski@city.cleveland.oh.us please set up meeting w/ Council member to discuss bus stop locations | Clay Harris | 07/15/21 1:54 PM
| Meeting scheduled. | Clay Harris | 07/22/21 1:56 PM
Row 52 | Sidewalk abuts buildings. Need to develop process to address. | Clay Harris | 03/27/20 3:01 PM
Row 57 | Need State to update bridge inspection info on E. 89th. | Clay Harris | 06/09/23 1:29 PM
Row 57 | Need list of streets resurfaced so we can add to moritorium list | Clay Harris | 05/05/23 3:07 PM
Row 57 | Need as build drawings and inventory/baseline inspection on 89th Street bridge. | Clay Harris | 03/31/23 1:05 PM
Row 57 | @asanchez@clevelandohio.gov please confirm we have citizen complaints contact info. | Clay Harris | 07/26/22 1:08 PM
| spoke w/ citizen. ODOT to mow. | Clay Harris | 08/02/22 1:05 PM
Row 57 | @asanchez@clevelandohio.gov provide limits of streets so we can add in Cityworks | Clay Harris | 07/26/22 1:07 PM
Row 57 | @asanchez@city.cleveland.oh.us please reach out to DOS & see if Shelton is able to complete work | Clay Harris | 04/05/22 1:06 PM
Row 57 | Erika found agreements between ODOT and forwarded to Director for review. | Clay Harris | 01/13/22 1:06 PM
Row 57 | Need to determine maintenance responsibilities on corridor after project is turned over. | Clay Harris | 01/06/22 11:11 AM
Row 57 | Provide economic dev. information requested | Clay Harris | 08/15/19 1:07 PM
Row 57 | @asanchez@city.cleveland.oh.us Provide street condition assessment of detour routes before construction. | Clay Harris | 03/07/19 1:12 PM
Row 57 | Coordinate E 75th typical section w/ ODOT | Clay Harris | 09/27/18 1:10 PM
Row 58 | 3/22/22: Continuing with addressing concerns with Catts Aging Receivables. Working with contractor(s) to schedule work on task orders that were encumbered before the contract expired. | Erin Oneill | 03/22/22 1:48 PM
Row 58 | 2/22/22: Working on invoices, confirming memo, will resume work when the weather breaks per our 2/16 meeting with Law and Finance. | Erin Oneill | 02/22/22 11:12 AM
Row 58 | 10-14-21: Wards 3,5,9,11 and 12 are complete. Working on Wards 8, 10, 13, 15 and Gap Independence. | frank keehl | 10/14/21 12:43 PM
Row 58 | Wards 5,9 and 11 are complete. Ward 3 is substantially complete. 12 is in progress. Waiting for Wards 8, 10, and 13 financial approvals. Commerce and Lakeside are complete. Brick streets are complete. | frank keehl | 08/12/21 12:46 PM
Row 58 | Meeting w/ CM Brancatelli regarding work on Independance requests to increase limits to city limits. Informed him that is outside scope of residential resurfacing program. Rick for forward to Director for review and comment. | Clay Harris | 06/03/21 1:30 PM
Row 58 | submitted project to DPS in August. Need advertisement dates. | Clay Harris | 09/26/19 1:24 PM
Row 61 | County sponsored - Ivanhoe Project and Green Project will be bid together | Tom Boyer | 11/11/21 12:54 PM
Row 62 | County sponsored - Green Road Project and Ivanhoe Project will be bid together and be constructed in May 2022 to December 2022. | Tom Boyer | 11/11/21 12:54 PM
Row 63 | send out traffic advisory before work starts @rmason@clevelandohio.gov | Clay Harris | 03/29/22 1:35 PM
| complete | Clay Harris | 04/05/22 1:48 PM
Row 63 | Contractor claim for street sub grade. | Clay Harris | 10/15/21 1:32 PM
| done | Clay Harris | 03/15/22 2:02 PM
Row 63 | Project in accounts department for 5 weeks. Need contract executed soon so it can begin construction in March. | Clay Harris | 01/21/21 2:09 PM
Row 69 | 4/11/22: CATTS has finished almost all Open sidewalks. Working on rest of 50/50 properties and then working on remaining TDS properties. | Robert Knopf | 04/11/22 1:52 PM
Row 69 | 3/14/21: Contractor is working on safety issues (where sidewalk is removed first) and then finishing unstarted work within TOs previously given to them | Robert Knopf | 03/14/22 12:34 PM